## Sprint1
Sprint Backlog Template
Backlog Item | Story Points | Responsible | Status | Original Estimate | 2016-05-16 | 2016-05-17 | 2016-05-18 | 2016-05-19 | 2016-05-20 | 2016-05-23 | 2016-05-24 | 2016-05-25 | 2016-05-26 | 2016-05-27 | Sprint Review
User Story #1Home Page | 5
Design the home page for the website user with responsive css. |  | Dinesh | Completed | 2 | 2016-05-16: 2
Providing the different access button/links for the user(Feedback,Registration,Login) |  | Dinesh | Completed | 3 | 2016-05-16: 2
User Story #2Registration/Signup | 10
Design and develop of the user registration form/template using bootsrap css |  | Guru | Completed | 3 | 2016-05-17: 4
Code implemention at the backend to store the data on the mongodb serverTask |  | Guru | Completed | 7 | 2016-05-17: 1; 2016-05-18: 3
User Story #3Login/Logout | 10
Design and develop of the login & Logut form/template to authenticate the user over the site |  | Sreeharsha | Completed | 5 | 2016-05-17: 3
Code implemention to validate the user and authenticate with the site and provided the logout functionality |  | Sreeharsha | Completed | 5 | 2016-05-17: 2; 2016-05-18: 5
User Story #4Landing page | 5
Design and develop the home/landing page for the user once he/she loged in to the website |  | Dinesh | Completed | 3 | 2016-05-17: 3
Design and develop the layout for the user |  | Dinesh | Completed | 1 | bar: 2016-05-17
Provide the search template for the parent user to search for the zip code details |  | Dinesh | Completed | 1 | bar: 2016-05-17
User Story #5Profile Update | 10
Design and develop the template for the user to update the personal detail. |  | Sreeharsha | Completed | 4 | 2016-05-19: 4
Implement the functionality to update and store the data over database server. |  | Sreeharsha | Completed | 6 | 2016-05-20: 6
User Story #6Zipcode Search | 20
Implement the functionality to consume webservice exposed by CHHS to retrieve children's residential facilities based on Zip code |  | Guru | Completed | 20 | 2016-05-19: 5; 2016-05-20: 5; 2016-05-23: 5; 2016-05-24: 5
User Story #7Feedback feature | 5
Design and develop the template for the user to give their own feedback about the website. |  | Sreeharsha | Completed | 3 | 2016-05-23: 3
Implement the logic to store the feedback of the user on the database server. |  | Sreeharsha | Completed | 2 | 2016-05-23: 2
User Story #8Personal Messaging system | 15
Design the template for the user to communicate with other user |  | Sreeharsha | Completed | 2 | 2016-05-24: 2
Design and develop of mail composer functionality |  | Sreeharsha | Completed | 3 | 2016-05-24: 1; 2016-05-25: 3; 2016-05-26: 1 | 1
Design the template for reply for the message |  | Sreeharsha | Completed | 2 | 2016-05-26: 2; 2016-05-27: 1
Implemention of code logic for the personal mailing system |  | Sreeharsha | Overdue | 6 | 2016-05-27: 3 | 3
Restricted the parent user to communicate with case workers and vice-versa |  | Sreeharsha | Overdue | 2 | [10 empty] | 2
User Story #9Chat functionality | 15
Design the layout for the user to chat with other user |  | Guru | Completed | 4 | 2016-05-24: 4
Implementation of code logic to chat with the users |  | Guru | Overdue | 8 | 2016-05-25: 4; 2016-05-26: 5
Restricted the parent user to communicate with case workers and vice-versa over chat system |  | Guru | Overdue | 3 | [10 empty] | 3
Total |  |  |  | 95 | 4 | 15 | 8 | 9 | 11 | 10 | 12 | 7 | 8 | 4 | 9

## Sprint2
Backlog Item | Story Points | Responsible | Status | Original Estimate | 2016-05-30 | 06-31-2016 | 2016-06-01 | 2016-06-02 | 2016-06-03 | Sprint Review
User Story #8Personal Messaging system | 5
Implemention of code logic for the personal mailing system |  | Sreeharsha | Completed | 3 | 3 |  |  |  |  | 3
Restricted the parent user to communicate with case workers and vice-versa |  | Sreeharsha | Completed | 2 | 3 |  |  |  |  | 2
User Story #9Chat functionality | 3
Restricted the parent user to communicate with case workers and vice-versa over chat system |  | Guru | Overdue | 3 | [5 empty] | 3
User Story #9Bug Fixes | 15
DEF1,DEF4,DEF5
3
Total |  |  |  | 8 | 6 |  | 0 | 0 | 0 | 11