## Agile Project Plan
Agile Project Plan
Project Name | Product Release
Project Manager | Siddharth
Project Deliverable | ADPQ
Scope Statement
Start Date | 2016-05-16
End Date | 2016-06-03
Overall Progress | 100%
Task Name | Responsible | Start | End | Days | Status
Sprint 1 | Srinivas | 2016-05-16 | 2016-05-27 | 11 | Complete
Home Page Design | Dinesh | 2016-05-16 | 2016-05-17 | 1 | Complete
Registration/Signup | Guru | 2016-05-17 | 2016-05-19 | 2 | Complete
Login/Logout | Sreeharsha | 2016-05-17 | 2016-05-19 | 2 | Complete
Landing page design for users | Dinesh | 2016-05-17 | 2016-05-18 | 1 | Complete
Profile Update | Sreeharsha | 2016-05-19 | 2016-05-21 | 2 | Complete
Zipcode Search | Guru | 2016-05-19 | 2016-05-25 | 4 | Complete
Feedback feature | Sreeharsha | 2016-05-23 | 2016-05-24 | 1 | Complete
Personal Messaging system | Sreeharsha | 2016-05-25 | 2016-05-27 | 2 | Overdue
Chat functionality | Guru | 2016-05-25 | 2016-05-27 | 2 | Overdue
Sprint 2 | Srinivas | 2016-05-30 | 2016-06-03 | 4 | Complete
Personal Messaging system | Sreeharsha | 2016-05-30 | 2016-05-31 | 1 | Complete
Chat functionality | Guru | 2016-05-30 | 2016-05-31 | 1 | Complete
Bug Fixes | Guru | 2016-05-31 | 2016-06-01 | 1 | Complete
Deployment | Srinivas | 2016-06-02 | 2016-06-03 | 1 | Complete
Formulas:
Start = [Start, row below]